## Contributions
Contributor | Role | Phase | Task ID | Contribution Description | Hours (Est.) | Hours (Actual) | Status | Notes
Heath Blackmon | PI / Project Lead | 1 | P1.3 | Drafted preprint strategy and timeline | 8 |  | Complete
Heath Blackmon | PI / Project Lead | 2 | P2.4 | Phylogenetic placement & curation of 50 genomes (manual) | 12 |  | Pending
Heath Blackmon | PI / Project Lead | 2 | P2.6 | Validation of constraint tree topology | 4 |  | Pending
Heath Blackmon | PI / Project Lead | 3 | P3.1 | Setup ProgressiveCactus pipeline on Grace | 6 |  | Pending
Heath Blackmon | PI / Project Lead | 3 | P3.2 | Monitor alignment job; troubleshoot failures | 8 |  | Pending
Heath Blackmon | PI / Project Lead | 4 | P4.2 | Manual review of rearrangement calls (confirmed vs inferred) | 10 |  | Pending
Heath Blackmon | PI / Project Lead | 5 | P5.6 | Extensive editing of Results section and manuscript | 20 |  | Pending
Heath Blackmon | PI / Project Lead | 5 | All | Final review of all figures and data release | 15 |  | Pending
Claude (AI) | Code Generation | 1 | P1.1-1.2 | Literature search queries & summary templates |  |  | Pending | Human verification required
Claude (AI) | Code Generation | 2 | P2.1-2.2 | NCBI & Ensembl genome mining scripts |  |  | Pending
Claude (AI) | Code Generation | 2 | P2.3 | Deduplication & quality filtering script |  |  | Pending
Claude (AI) | Code Generation | 2 | P2.6 | Phylogenetic tree inference script |  |  | Pending
Claude (AI) | Code Generation | 3 | P3.1 | HPC pipeline setup (SLURM, ProgressiveCactus) |  |  | Pending
Claude (AI) | Code Generation | 3 | P3.3 | Synteny extraction from HAL alignment |  |  | Pending
Claude (AI) | Code Generation | 4 | P4.1-4.6 | Rearrangement calling, filtering, mapping, stats, karyotypes |  |  | Pending
Claude (AI) | Code Generation | 5 | P5.1-5.6 | All visualizations, data release, Results draft |  |  | Pending
[Student TBD] | [TBD] |  |  | [To be assigned]

## Authorship Criteria
ICMJE Criterion | Heath Blackmon | Claude (AI) | Student TBD | Other TBD
1. Conception/Design | YES | Partial
2. Data Acquisition | YES | YES
3. Analysis/Interpretation | YES | YES (code only)
4. Manuscript Draft | YES | YES (draft)
5. Critical Revision | YES | Limited
6. Final Approval | YES | NO
7. Accountability | YES | NO
MEETS ALL CRITERIA? | YES - First Author | NO - Acknowledge

## Summary
Contributor | Role | Total Est. Hours | Total Actual Hours | Recommended Authorship
Heath Blackmon | PI | 83 | 0 | First Author
Claude (AI) | Code Generation | N/A (AI) | N/A | Acknowledged
[Student TBD] | [TBD] | 0 | 0 | [TBD]

## Acknowledgments Text
ACKNOWLEDGMENTS SECTION (for Preprint)
We thank [colleagues, funding sources, institutional resources]. Computational assistance was provided by Claude (Anthropic), an AI language model. All code was reviewed and validated by H.B. before use. A detailed log of AI-generated contributions and review procedures is provided in supplementary materials (ai_use_log.xlsx and ai_code_review_checklist.xlsx). This work was supported by [funding sources] and computational resources provided by Texas A&M HPRC (Grace HPC).